## Sheet1
Assignment | Online Shopping Application |  |  |  | Estimator | Thamasha
Assignment Type | Development |  |  |  | Reviewed by
Review Date
Total Effort Estimate (Hours) | 432.2
No. | Task Name | Task Type | Optimistic Effort (P Hours) | Most Likely Effort (P Hours) | Pessimistic Effort (P Hours) | 3P Estimated Effort (P Hours)
1 | Common- Requirements Discovery
2 | Requirement Development | Requirements Dev | 16.8 | 24 | 36 | 25.6
3 | Requirement Review | Requirements Review
4 | Requirement Rework | Requirements Rework | 0.7 | 1 | 1.5 | 1.1
5
6 | Common- Database
7 | DB Design | DB Design | 4.2 | 6 | 9 | 6.4
8 | DB Design Review | DB Design Review
9 | DB Design Rework | DB Design Rework | 0.7 | 1 | 1.5 | 1.1
10 | DB Development | DB Development | 11.2 | 16 | 24 | 17.1
11 | DB Review | DB Review
12 | DB Rework | DB Rework | 0.7 | 1 | 1.5 | 1.1
13
14 | Feature 1: Login
15 | Design | Design Development | 1.4 | 2 | 3 | 2
16 | Design Review | Design Review
17 | Design Rework | Design Rework | 0.7 | 1 | 1.5 | 1.1
18 | Data Access Layer Development | Code Development | 4.2 | 6 | 9 | 6.4
19 | Business Layer Development | Code Development | 4.2 | 6 | 9 | 6.4
20 | Service Layer Development | Code Development | 4.2 | 6 | 9 | 6.4
21 | Web Client Development | Code Development | 7 | 10 | 15 | 10.6
22 | Developer Testing | Dev Testing | 1.4 | 2 | 3 | 2
23 | Unit Testing | Code Development | 3.5 | 5 | 7.5 | 5.3
24 | Code Review | Code Review
25 | Code Rework | Code Rework | 1.4 | 2 | 3 | 2
26
27 | Feature 2: Register Customer
28 | Design | Design Development | 1.4 | 2 | 3 | 2
29 | Design Review | Design Review
30 | Design Rework | Design Rework | 0.7 | 1 | 1.5 | 1.1
31 | Data Access Layer Development | Code Development | 4.2 | 6 | 9 | 6.4
32 | Business Layer Development | Code Development | 4.2 | 6 | 9 | 6.4
33 | Service Layer Development | Code Development | 4.2 | 6 | 9 | 6.4
34 | Web Client Development | Code Development | 7 | 10 | 15 | 10.6
35 | Developer Testing | Dev Testing | 1.4 | 2 | 3 | 2
36 | Unit Testing | Code Development | 3.5 | 5 | 7.5 | 5.3
37 | Code Review | Code Review
38 | Code Rework | Code Rework | 1.4 | 2 | 3 | 2
39
40 | Feature 3: View Product/ Categories
41 | Design | Design Development | 1.4 | 2 | 3 | 2
42 | Design Review | Design Review
43 | Design Rework | Design Rework | 0.7 | 1 | 1.5 | 1.1
44 | Data Access Layer Development | Code Development | 4.2 | 6 | 9 | 6.4
45 | Business Layer Development | Code Development | 4.2 | 6 | 9 | 6.4
46 | Service Layer Development | Code Development | 4.2 | 6 | 9 | 6.4
47 | Web Client Development | Code Development | 7 | 10 | 15 | 10.6
48 | Developer Testing | Dev Testing | 1.4 | 2 | 3 | 2
49 | Unit Testing | Code Development | 3.5 | 5 | 7.5 | 5.3
50 | Code Review | Code Review
51 | Code Rework | Code Rework | 1.4 | 2 | 3 | 2
52
53 | Feature 4: Add Products to the cart
54 | Design | Design Development | 1.4 | 2 | 3 | 2
55 | Design Review | Design Review
56 | Design Rework | Design Rework | 0.7 | 1 | 1.5 | 1.1
57 | Data Access Layer Development | Code Development | 4.2 | 6 | 9 | 6.4
58 | Business Layer Development | Code Development | 4.2 | 6 | 9 | 6.4
59 | Service Layer Development | Code Development | 4.2 | 6 | 9 | 6.4
60 | Web Client Development | Code Development | 7 | 10 | 15 | 10.6
61 | Developer Testing | Dev Testing | 1.4 | 2 | 3 | 2
62 | Unit Testing | Code Development | 3.5 | 5 | 7.5 | 5.3
63 | Code Review | Code Review
64 | Code Rework | Code Rework | 1.4 | 2 | 3 | 2
65
66 | Feature 5: Remove/ Modify products in the cart
67 | Design | Design Development | 1.4 | 2 | 3 | 2
68 | Design Review | Design Review
69 | Design Rework | Design Rework | 0.7 | 1 | 1.5 | 1.1
70 | Data Access Layer Development | Code Development | 4.2 | 6 | 9 | 6.4
71 | Business Layer Development | Code Development | 4.2 | 6 | 9 | 6.4
72 | Service Layer Development | Code Development | 4.2 | 6 | 9 | 6.4
73 | Web Client Development | Code Development | 7 | 10 | 15 | 10.6
74 | Developer Testing | Dev Testing | 1.4 | 2 | 3 | 2
75 | Unit Testing | Code Development | 3.5 | 5 | 7.5 | 5.3
76 | Code Review | Code Review
77 | Code Rework | Code Rework | 1.4 | 2 | 3 | 2
78
79 | Feature 6: Checkout
80 | Design | Design Development | 1.4 | 2 | 3 | 2
81 | Design Review | Design Review
82 | Design Rework | Design Rework | 0.7 | 1 | 1.5 | 1.1
83 | Data Access Layer Development | Code Development | 4.2 | 6 | 9 | 6.4
84 | Business Layer Development | Code Development | 4.2 | 6 | 9 | 6.4
85 | Service Layer Development | Code Development | 4.2 | 6 | 9 | 6.4
86 | Web Client Development | Code Development | 7 | 10 | 15 | 10.6
87 | Developer Testing | Dev Testing | 1.4 | 2 | 3 | 2
88 | Unit Testing | Code Development | 3.5 | 5 | 7.5 | 5.3
89 | Code Review | Code Review
90 | Code Rework | Code Rework | 1.4 | 2 | 3 | 2
91
92 | Feature 7: View Bill
93 | Design | Design Development | 1.4 | 2 | 3 | 2
94 | Design Review | Design Review
95 | Design Rework | Design Rework | 0.7 | 1 | 1.5 | 1.1
96 | Data Access Layer Development | Code Development | 4.2 | 6 | 9 | 6.4
97 | Business Layer Development | Code Development | 4.2 | 6 | 9 | 6.4
98 | Service Layer Development | Code Development | 4.2 | 6 | 9 | 6.4
99 | Web Client Development | Code Development | 7 | 10 | 15 | 10.6
100 | Developer Testing | Dev Testing | 1.4 | 2 | 3 | 2
101 | Unit Testing | Code Development | 3.5 | 5 | 7.5 | 5.3
102 | Code Review | Code Review
103 | Code Rework | Code Rework | 1.4 | 2 | 3 | 2
104
105 | Feature 8: Email bill to the customer
106 | Design | Design Development | 1.4 | 2 | 3 | 2
107 | Design Review | Design Review
108 | Design Rework | Design Rework | 0.7 | 1 | 1.5 | 1.1
109 | Data Access Layer Development | Code Development | 4.2 | 6 | 9 | 6.4
110 | Business Layer Development | Code Development | 4.2 | 6 | 9 | 6.4
111 | Service Layer Development | Code Development | 4.2 | 6 | 9 | 6.4
112 | Web Client Development | Code Development | 7 | 10 | 15 | 10.6
113 | Developer Testing | Dev Testing | 1.4 | 2 | 3 | 2
114 | Unit Testing | Code Development | 3.5 | 5 | 7.5 | 5.3
115 | Code Review | Code Review
116 | Code Rework | Code Rework | 1.4 | 2 | 3 | 2
117
118 | Feature 9: View Payment History
119 | Design | Design Development | 1.4 | 2 | 3 | 2
120 | Design Review | Design Review
121 | Design Rework | Design Rework | 0.7 | 1 | 1.5 | 1.1
122 | Data Access Layer Development | Code Development | 4.2 | 6 | 9 | 6.4
123 | Business Layer Development | Code Development | 4.2 | 6 | 9 | 6.4
124 | Service Layer Development | Code Development | 4.2 | 6 | 9 | 6.4
125 | Web Client Development | Code Development | 7 | 10 | 15 | 10.6
126 | Developer Testing | Dev Testing | 1.4 | 2 | 3 | 2
127 | Unit Testing | Code Development | 3.5 | 5 | 7.5 | 5.3
128 | Code Review | Code Review
129 | Code Rework | Code Rework | 1.4 | 2 | 3 | 2